# Coxa Fan OS

CDP & Data Intelligence Platform

AI-Accelerated Development Plan

Data Warehouse | CDP Events | Personalization | Segmentation

Prepared: July 2026

Client: Coritiba FC / Coxa Fan OS

Development Model: Full AI-Assisted (Cursor Agents + LLMs)

Timeline: 8 weeks (4 phases, AI-accelerated)

Classification: Internal — Engineering Strategy

# 1. Executive Summary

This document outlines an AI-accelerated 8-week implementation plan to evolve the Coxa Fan OS platform into an enterprise-grade data intelligence system. By leveraging AI coding agents (Cursor, Claude, GPT-4o) for end-to-end development — code generation, test writing, configuration, documentation — the timeline is compressed from the traditional 16 weeks to 8 weeks without sacrificing quality.

AI Development Model:

- AI agents generate 80-90% of implementation code (services, models, routes, UI components)

- AI writes unit tests, integration tests, and test fixtures

- AI generates infrastructure configs (Docker, Airbyte, Cube models, Dagster pipelines)

- AI handles documentation, API specs, and migration scripts

- Human developers review, validate architectural decisions, and run acceptance tests

- Human handles cloud provisioning, secrets management, and production deployment

Why 8 weeks (not faster):

- Infrastructure provisioning has real-world latency (cloud setup, DNS, networking)

- Airbyte initial data sync takes time regardless of code speed

- ML models need real historical data to train — cannot be accelerated

- Testing gates require human verification and stakeholder sign-off

- Integration testing surfaces real bugs that need debugging cycles

Deliverables (same scope, compressed timeline):

- Redis Streams event backbone (async, resilient, scalable)

- ClickHouse analytical warehouse + Airbyte CDC + Dagster orchestration

- Cube semantic layer replacing static KPI registry

- Advanced segmentation (AND/OR/NOT, ClickHouse-backed, visual builder)

- ML scoring pipeline (churn, ticket propensity, retail propensity, next-best-channel)

- ML-ranked personalization with frequency capping and A/B testing

- AI campaign generation with human-in-the-loop approval

# 2. AI-Accelerated Development Model

## 2.1 How AI Agents Are Used Per Task Type

| Task Type | AI Role | Human Role | Speed Multiplier |
| --- | --- | --- | --- |
| Backend services (Node.js) | Generates full service code, tests, error handling | Reviews architecture, validates logic | 5-8x |
| API routes + middleware | Generates routes, validation, docs, OpenAPI specs | Reviews auth/security patterns | 6-10x |
| Mongoose models + migrations | Generates schemas, indexes, validators | Confirms data model decisions | 8-10x |
| React UI pages | Generates full pages with state, API calls, UX | Reviews UX flow, visual QA | 4-6x |
| Infrastructure configs | Generates Docker, YAML, Cube models, Dagster DAGs | Validates deployment constraints | 5-8x |
| ML pipeline (Python) | Generates feature engineering, model training code | Validates model performance, tunes | 3-5x |
| Tests (unit + integration) | Generates comprehensive test suites | Runs, validates edge cases | 8-12x |
| Documentation | Generates API docs, architecture docs, runbooks | Reviews for accuracy | 10-15x |

## 2.2 Development Workflow Per Feature

- 1. Human defines requirements + acceptance criteria (15 min)

- 2. AI agent generates implementation (code + tests + docs) (30-60 min)

- 3. Human reviews generated code, requests adjustments (15-30 min)

- 4. AI agent fixes issues, adds edge cases (10-20 min)

- 5. Human runs integration tests, validates against acceptance criteria (30 min)

- 6. Merge + deploy to staging (automated CI)

Average feature cycle: 2-3 hours (vs 1-2 days traditional)

## 2.3 Quality Controls

- AI-generated code passes linting (ESLint) before human review

- AI writes tests with > 80% coverage for new code

- All AI output reviewed by senior developer before merge

- Integration tests run on every PR (automated)

- Performance benchmarks validated at each phase gate

- Security review of auth/data-access patterns by human

# 3. Compressed Timeline (8 Weeks)

| Phase | Duration | Focus | AI Handles | Human Handles |
| --- | --- | --- | --- | --- |
| Phase 1 | Week 1-2 | Event Streaming Backbone | Event schema, eventBus refactor, worker extension, error isolation, tests | Redis infra validation, load testing |
| Phase 2 | Week 3-5 | Data Warehouse + Semantic Layer | ClickHouse schemas, Cube models, analytics migration, Dagster pipelines | Cloud provisioning, Airbyte config, data parity validation |
| Phase 3 | Week 5-7 | Segmentation + ML Scoring | Rule engine v2, SQL compiler, segment UI, ML feature code, model training scripts | Model evaluation, hyperparameter tuning, UI acceptance |
| Phase 4 | Week 7-8 | Personalization + AI Activation | NBO ranking, frequency cap, A/B framework, AI campaign service, approval UI | End-to-end validation, stakeholder demo |

Note: Phases overlap by 1 week — AI starts next phase code while humans validate current phase.

# 4. Phase 1: Event Streaming Backbone (Weeks 1-2)

Traditional: 4 weeks | AI-Accelerated: 2 weeks

## 4.1 Week 1 — AI Generates Core Infrastructure

| Day | AI Delivers | Human Validates |
| --- | --- | --- |
| Day 1 | packages/events/ — typed schema for 30+ events, publisher/consumer SDK | Review type definitions, naming |
| Day 2 | Refactored eventBus.js — async Redis Stream publish, non-blocking | Test existing event flow still works |
| Day 3 | Extended worker.js — consumer group, XREADGROUP loop, auto-claim | Verify consumer group mechanics |
| Day 4 | Upgraded eventProcessors.js — Promise.allSettled isolation | Run processor failure scenarios |
| Day 5 | Stream health endpoint, DLQ management, retry logic | Review monitoring/alerting approach |

## 4.2 Week 2 — Testing + Hardening

| Day | AI Delivers | Human Validates |
| --- | --- | --- |
| Day 1-2 | Full test suite (unit + integration) for event pipeline | Run tests, verify coverage > 80% |
| Day 3 | Load test scripts (1000 events/min for 30 min) | Execute load test, monitor Redis |
| Day 4 | DLQ replay tests, crash recovery scenarios | Validate recovery behavior |
| Day 5 | Documentation, monitoring dashboard config | Sign-off: Phase 1 complete |

## 4.3 Phase 1 Gate Criteria

| Test | Target |
| --- | --- |
| Event ingestion latency | < 50ms HTTP response |
| Processing time | Side-effects within 2s of publish |
| Load test | 1000 events/min sustained 30 min |
| DLQ recovery | Failed events replayable |
| Error isolation | One processor failure doesn't block others |
| Test coverage | > 80% on new code |

# 5. Phase 2: Data Warehouse & Semantic Layer (Weeks 3-5)

Traditional: 5 weeks | AI-Accelerated: 3 weeks

## 5.1 Week 3 — Infrastructure + Schema

| Day | AI Delivers | Human Handles |
| --- | --- | --- |
| Day 1 | docker-compose.analytics.yml (ClickHouse + Airbyte + Cube + Dagster) | Deploy, verify connectivity |
| Day 2 | ClickHouse table schemas (events, sales, tickets, fan_360, MVs) | Review partitioning strategy |
| Day 3 | Airbyte connection configs (JSON) for 7 MongoDB collections | Configure in Airbyte UI, start initial sync |
| Day 4-5 | Dagster pipeline definitions (sync health, refresh schedules) | Verify Dagster UI, check schedules |

## 5.2 Week 4 — Cube + Migration

| Day | AI Delivers | Human Handles |
| --- | --- | --- |
| Day 1-2 | Cube semantic models — all ~80 KPIs ported from kpiRegistry.js | Validate KPI definitions against business logic |
| Day 3 | cubeClient.js — Cube REST API wrapper for Node.js backend | Integration test against live Cube |
| Day 4 | Refactored fanboxAnalyticsService.js — reads Cube (MongoDB fallback) | Compare old vs new results |
| Day 5 | New endpoint: GET /api/v1/reporting/kpis (flexible query) | Test with dashboard team |

## 5.3 Week 5 — Validation + Cutover

| Day | AI Delivers | Human Handles |
| --- | --- | --- |
| Day 1-2 | Integration test suite: data parity checks (old vs new) | Run parity validation across all 8 depts |
| Day 3 | Performance test scripts (1-year range queries) | Verify < 500ms response time |
| Day 4 | Updated InsightsPage.jsx — connected to Cube API | Visual QA, stakeholder review |
| Day 5 | Documentation, runbook for analytics stack | Sign-off: Phase 2 complete |

## 5.4 Technology Summary

| Tool | What It Does | Why It Fits Coxa |
| --- | --- | --- |
| ClickHouse | Columnar OLAP — sub-second aggregation over millions of rows | 10-100x faster than MongoDB for analytics; matchday event volumes |
| Airbyte | ELT with MongoDB CDC connector — incremental 15-min syncs | Zero custom ETL; handles schema evolution automatically |
| Cube | Semantic layer — define KPIs once, query via REST/GraphQL | Replaces static kpiRegistry.js; caching + pre-aggregations |
| Dagster | Pipeline orchestration — schedules, retries, observability | Orchestrates sync → transform → ML → scoring; lighter than Airflow |

# 6. Phase 3: Advanced Segmentation & ML (Weeks 5-7)

Traditional: 4 weeks | AI-Accelerated: 2.5 weeks (overlaps Phase 2 by 1 week)

## 6.1 Segmentation Engine v2

AI generates the complete rule engine rewrite:

- New Segment schema with nested rule groups (match: all/any/none)

- segmentQueryBuilder.js — compiles rule tree to ClickHouse SQL WHERE clause

- Updated segmentService.js — evaluates via ClickHouse (not in-memory scan)

- Scheduled segment refresh via Dagster (hourly re-evaluation)

- WebSocket live-counter as rules change (debounced query)

Segment UI (AI-generated React):

- Visual AND/OR/NOT tree with drag-and-drop nesting

- Live audience counter updating as rules change

- Segment comparison (Venn overlap)

- Trait browser with distributions

## 6.2 ML Scoring Pipeline

AI generates Python pipeline code; human validates model performance:

| Model | AI Generates | Human Validates | Target AUC |
| --- | --- | --- | --- |
| Churn prediction | Feature SQL, XGBoost training code, scoring script | Model evaluation, threshold tuning | > 0.70 |
| Ticket propensity | Event-specific features, training pipeline | Per-event scoring validation | > 0.65 |
| Retail propensity | Purchase history features, training | Recommendation quality check | > 0.65 |
| Next-best-channel | Channel engagement features, multi-class model | Channel ranking validation | > 0.60 |

Architecture: Feature store (ClickHouse) → Training (Python/XGBoost in Dagster) → Nightly batch scoring → Writeback to MongoDB FanProfile

## 6.3 Phase 3 Gate Criteria

| Test | Target |
| --- | --- |
| Backward compatibility | Existing AND-only segments identical results |
| Nested logic | Complex OR/NOT rules evaluate correctly |
| Segment preview | < 1 second for 100K+ fans |
| Churn model AUC | > 0.70 on test set |
| Score freshness | Updated within 6 hours |
| UI acceptance | Segment builder usable by non-engineer |

# 7. Phase 4: Personalization & AI Activation (Weeks 7-8)

Traditional: 3 weeks | AI-Accelerated: 2 weeks (overlaps Phase 3 by 1 week)

## 7.1 ML-Ranked Personalization

AI generates the complete NBO v2 system:

- Scoring function: segment match + propensity + recency penalty + conversion rate

- Top-3 ranked offers with confidence scores

- OfferImpression model for tracking

- Frequency capping rules (configurable per tenant)

- A/B variant assignment (deterministic hash)

## 7.2 AI Campaign Engine

- aiCampaignService.js — LLM analyzes segments + scores + KPIs

- Identifies opportunities (high-churn, lapsed, birthday, event-triggered)

- Drafts campaigns: segment, channel, timing, offer, LLM-generated copy

- Approval queue with auto-launch below risk threshold

- Result tracking + reinforcement feedback loop

## 7.3 Phase 4 Gate Criteria

| Test | Target |
| --- | --- |
| NBO response | Returns 3 ranked offers in < 200ms |
| Frequency cap | Enforced correctly across channels |
| A/B determinism | Same fan always gets same variant |
| AI campaign | Generates valid draft with real segment |
| End-to-end | Event → offer delivery < 5 minutes |
| Approval flow | Approve/edit/reject workflow complete |

# 8. Open-Source Technology Research

| Tool | Stars | License | How It Works | Integration |
| --- | --- | --- | --- | --- |
| Redis Streams | Part of Redis | BSD-3 | Append-only log + consumer groups + ACK | ioredis (already installed) |
| ClickHouse | ~48,400 | Apache-2.0 | Columnar OLAP, vectorized SIMD execution | @clickhouse/client npm |
| Airbyte | ~21,600 | Elv2 | MongoDB CDC → ClickHouse, 15-min incremental | Docker + REST API |
| Cube | ~20,300 | Apache-2.0 | Semantic layer, pre-agg, REST/GraphQL API | @cubejs-client/core npm |
| Dagster | ~15,800 | Apache-2.0 | Asset-centric orchestration, native integrations | Python + Docker |
| Superset | ~73,600 | Apache-2.0 | Interactive BI, 50+ charts, embedded SDK | Connects to ClickHouse |
| XGBoost | ~27,000 | Apache-2.0 | Gradient-boosted trees for tabular ML | Python in Dagster |

# 9. Complete 8-Week Timeline

| Week | Phase | AI Delivers | Human Validates | Milestone |
| --- | --- | --- | --- | --- |
| 1 | Phase 1 | Event schema, async eventBus, worker consumer, error isolation | Architecture review | Stream publishing live |
| 2 | Phase 1 | Test suite, load tests, DLQ management, docs | Load test execution, sign-off | PHASE 1 COMPLETE |
| 3 | Phase 2 | Docker infra, ClickHouse schemas, Airbyte configs, Dagster DAGs | Deploy, start data sync | Infrastructure live |
| 4 | Phase 2 | Cube models (80 KPIs), cubeClient, analytics migration | KPI parity validation | Semantic layer live |
| 5 | Phase 2+3 | Parity tests, segment rule engine v2, SQL compiler | Phase 2 sign-off, segment review | PHASE 2 COMPLETE |
| 6 | Phase 3 | Segment UI v2, ML feature store, model training code | Model evaluation, UI acceptance | ML models trained |
| 7 | Phase 3+4 | Scoring pipeline, NBO v2, frequency cap, A/B framework | Phase 3 sign-off, NBO testing | PHASE 3 COMPLETE |
| 8 | Phase 4 | AI campaign service, approval queue, approval UI, e2e tests | End-to-end validation, demo | PHASE 4 COMPLETE |

# 10. Risk Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| AI-generated code quality | Bugs in production | Mandatory human review + automated test gates |
| AI hallucination in configs | Broken infrastructure | Validate all infra configs in staging before prod |
| Redis Streams capacity | Event loss on matchday | Monitor XLEN; documented Kafka upgrade path |
| Airbyte sync lag | Stale dashboards | 15-min SLA + Dagster alerting + MongoDB fallback |
| ML model accuracy | Bad recommendations | High action thresholds; human approval for campaigns |
| Segment regression | Existing segments break | AND-only = match:'all' (backward compatible) |
| LGPD compliance | Regulatory risk | PII masked in warehouse; consent enforcement |
| Timeline pressure | Cut corners | Phase gates are non-negotiable; no skip to next phase |

# 11. Team Requirements (AI-Augmented)

| Role | Responsibility | FTE | AI Amplification |
| --- | --- | --- | --- |
| Senior Backend Lead | Architecture decisions, code review, integration testing | 1.0 | Reviews AI output; 5x throughput |
| Data Engineer | ClickHouse/Airbyte/Dagster deployment + validation | 0.5 | AI generates configs; human deploys |
| ML Engineer | Model evaluation, hyperparameter tuning, validation | 0.5 (weeks 5-8 only) | AI generates pipeline; human tunes |
| Frontend Developer | Segment UI review, visual QA | 0.5 (weeks 5-8 only) | AI generates React; human QAs |
| DevOps | Cloud provisioning, CI/CD, secrets | 0.25 | AI generates Docker/IaC; human applies |

Total: ~2.75 FTE over 8 weeks (vs ~5 FTE over 16 weeks traditional)

AI agents effectively replace 3-4 additional developers while maintaining quality through human review gates.

# 12. Cost & Efficiency Comparison

| Metric | Traditional (No AI) | AI-Accelerated |
| --- | --- | --- |
| Timeline | 16 weeks | 8 weeks |
| Team size | 5 FTE | 2.75 FTE |
| Total person-weeks | 80 | 22 |
| Code generation speed | ~100 LOC/day per dev | ~800-1500 LOC/day with AI |
| Test writing | 30% of dev time | AI-generated, human-validated |
| Documentation | Often deferred | Generated alongside code |
| Risk of scope creep | High (16 weeks) | Lower (compressed timeline) |

# 13. Conclusion

Full AI-assisted development compresses this project from 16 weeks to 8 weeks — a 50% reduction — while maintaining the same scope and quality standards. The key insight is that AI excels at the high-volume, pattern-based work (service code, tests, configs, models) while humans focus on the judgment-intensive work (architecture, security, deployment, validation).

The 8-week timeline is achievable because:

- AI generates code 5-10x faster than manual development

- Tests are written simultaneously with implementation (not after)

- Infrastructure configs generated from specifications (not hand-crafted)

- Documentation is a by-product, not a separate phase

- Phase overlaps recover 2 weeks (AI starts next while humans validate current)

The timeline is NOT faster than 8 weeks because:

- Cloud infrastructure has real provisioning latency

- Data sync (Airbyte initial load) takes wall-clock time

- ML models need historical data and training iterations

- Human validation and stakeholder sign-off cannot be parallelized away

- Integration bugs surface only at runtime

Prepared by: Coxa Engineering

Development Model: AI-Accelerated (Cursor + Claude + GPT-4o)

Date: July 2026

Next review: End of Phase 1 (Week 2)