# FanBox Parity

Detailed Tasks Document

Source: Manual do FanBox · Coritiba SAF v1.0 · Generated June 11, 2026

PROJECT DEADLINE: Friday, 20 June 2026 (EOD)

Schedule: 10 June 2026 → 20 June 2026 · 8 working days

Source: Manual do FanBox · Coritiba SAF · v1.0 · 03/06/2026 (Manual_FanBox_CoritibaSAF.pdf)

Target platform: Coxa Fan OS (club-dashboard, club-auth, backend, fan-dashboard, fan-app)

Purpose: Translate every FanBox operational capability into actionable engineering tasks for Coxa, with gap analysis against what already exists in this repository.

Project deadline: Friday, 20 June 2026 (EOD) — all phases must be complete by end of next week.

Schedule window: 10 June 2026 → 20 June 2026 (8 working days)

Related docs: PROJECT_OVERVIEW.md · CLIENT_FEATURES.md · RETAIL_TIER_A_IMPLEMENTATION_PLAN.md

## 1. Executive summary

FanBox is Coritiba SAF’s fan intelligence and marketing operations platform. Coxa already implements several foundational modules (CDP, Customer 360, segments, membership, ticketing, retail, F&B, loyalty, personalization). This document maps FanBox’s 8 operational sections to Coxa work items and identifies what is done, partial, or missing.

| FanBox section | Coxa equivalent (today) | Parity status |
| --- | --- | --- |
| 01 — Informações Básicas | club-auth, DashboardLayout, RBAC | Partial — login exists; global fan counters and FanBox-style nav grouping missing |
| 02 — Dashboard Inicial | OverviewPage | Partial — module cards only; no growth charts, engagement/spend reports, CSV export |
| 03 — Meus Fãs | CdpCustomer360Page, MemberDetailPage | Partial — search limited; no engagement/personal-info aggregate dashboards |
| 04 — Negócios | Retail, F&B, Membership, Ticketing modules | Partial — operational UIs exist; no unified “Negócios” analytics layer with demographic breakdowns |
| 05 — Projetos Digitais | — | Missing — surveys, votes, raffles, contests, NPS |
| 06 — Fan Intelligence | CdpSegmentsPage | Partial — basic trait filters; no saved filter library, export, or “Meus Insights” |
| 07 — Campanhas | CampaignParticipation model only | Missing — no campaign builder, templates, scheduling, or delivery analytics |
| 08 — Painel de Controle | UsersPage, RolesPage | Partial — user management exists; no CSV import pipeline |

### Recommended delivery phases

| Phase | Scope | Outcome | Deadline |
| --- | --- | --- | --- |
| P0 — Shell & data foundation | Global counters, FanBox nav IA, fan profile enrichment schema, import pipeline | Platform feels like FanBox; data can be loaded | Thu 12 Jun 2026 |
| P1 — Analytics core | Dashboard charts, Negócios reports, engagement/personal-info screens | Staff can monitor base health and business KPIs | Mon 16 Jun 2026 |
| P2 — Fan Intelligence++ | Advanced filters, saved filters, CSV export, insights dashboard | Marketing can segment and export audiences | Wed 18 Jun 2026 |
| P3 — Projetos Digitais | Surveys, votes, raffles, contests, NPS | Direct fan engagement + trait enrichment | Thu 19 Jun 2026 |
| P4 — Campanhas | Email/push campaigns, templates, scheduling, analytics | Mass communication from filtered audiences | Fri 20 Jun 2026 |

### Sprint calendar (deadline: 20 Jun 2026)

| Dates | Focus | Must ship |
| --- | --- | --- |
| 10–12 Jun (Wed–Fri) | P0 — foundation | Profile schema, CSV import MVP, fan counters, FanBox sidebar, expanded fan search |
| 13–16 Jun (Mon–Mon) | P1 — analytics | Growth chart, engagement/spend reports, Single Fan View rows, Negócios shell + top 5 business reports |
| 17–18 Jun (Tue–Wed) | P2 — intelligence | Saved filters, CSV export, Meus Insights, segment bridge |
| 19 Jun (Thu) | P3 — digital projects | Survey + vote + raffle MVP; contest/NPS stubs acceptable if time-constrained |
| 20 Jun (Fri) | P4 — campaigns + hardening | Campaign wizard, template list, send/schedule MVP, smoke tests, doc sign-off |

Daily standup checkpoint: blockers escalated same day; any phase slipping past its milestone date triggers scope cut to MVP (see Out of scope fallbacks below).

MVP fallback if behind schedule (still due 20 Jun): defer TASK-04-06 through 04-11 (App/OTT/Coxa Run integrations), TASK-05-04/05-05 (contests/NPS), and TASK-07-05 drag-and-drop builder (HTML template import only).

## 2. FanBox → Coxa module mapping

flowchart LR
  subgraph fanbox [FanBox Manual Sections]
    FB1[01 Básicas]
    FB2[02 Dashboard]
    FB3[03 Meus Fãs]
    FB4[04 Negócios]
    FB5[05 Projetos]
    FB6[06 Intelligence]
    FB7[07 Campanhas]
    FB8[08 Painel]
  end

  subgraph coxa [Coxa Modules]
    AUTH[club-auth]
    CD[club-dashboard]
    CDP[CDP / Traits]
    MEM[Membership]
    TIX[Ticketing]
    RET[Retail]
    FNB[F&B]
    LOY[Loyalty]
    PER[Personalization]
    BE[backend API]
  end

  FB1 --> AUTH
  FB1 --> CD
  FB2 --> CD
  FB3 --> CDP
  FB3 --> MEM
  FB4 --> RET
  FB4 --> FNB
  FB4 --> TIX
  FB4 --> MEM
  FB5 --> BE
  FB6 --> CDP
  FB7 --> BE
  FB8 --> CD

## 3. Section 01 — Informações Básicas

FanBox reference: login URL, lateral menu structure, and global system counters (total fans, fans with CPF, email, phone, address) visible on every screen.

### 3.1 Current state in Coxa

| Item | Status | Location |
| --- | --- | --- |
| Login (email + password) | Done | apps/club-auth, backend/src/routes/auth.js |
| Post-login redirect to home | Done | ProtectedRoute, OverviewPage |
| Lateral sidebar menu | Done | DashboardLayout.jsx — grouped by Coxa modules (Retail, CDP, etc.), not FanBox IA |
| Global fan counters | Missing | — |
| Persistent counter bar on all pages | Missing | — |

### 3.2 Tasks

#### TASK-01-01 — Global fan counter API

Priority: P0 · Effort: M

☐ Create GET /api/v1/analytics/fan-counters returning:

totalFans — all active FanProfile records for tenant

withCpf — profiles where cpf (or national ID field) is present

withEmail — non-empty email

withPhone — non-empty phone

withAddress — address object complete (street + city minimum)

☐ Extend FanProfile schema with demographic/contact fields required by FanBox (see TASK-03-04)

☐ Add MongoDB indexes for counter aggregation performance

☐ Wire route behind requireAuth + requireModule(CDP) or global club-admin access

Acceptance criteria: API returns accurate counts within 2s for 100k profiles; counts update after profile create/update/import.

#### TASK-01-02 — Persistent counter bar in club-dashboard shell

Priority: P0 · Effort: S

☐ Add FanCounterBar component below sidebar brand or above main content

☐ Fetch counters on layout mount; refresh on club switch

☐ Display: Total fans · CPF · E-mail · Telefone · Endereço (labels configurable per locale)

☐ Match FanBox visual hierarchy (purple highlight in manual — use Coxa design tokens)

Acceptance criteria: Counters visible on every authenticated page; no layout shift on load.

#### TASK-01-03 — Reorganize sidebar to FanBox information architecture

Priority: P0 · Effort: M

Restructure DashboardLayout.jsx nav to mirror FanBox sections while preserving RBAC module gates:

| FanBox menu | Coxa routes (proposed) |
| --- | --- |
| (home) Dashboard Inicial | / |
| Meus Fãs | /fans/single, /fans/engagement, /fans/profiles |
| Negócios | /business/* (sub-routes per source) |
| Projetos Digitais | /projects/* |
| Fan Intelligence | /intelligence/filters, /intelligence/insights |
| Campanhas | /campaigns/* |
| Painel de Controle | /control/users, /control/import |

☐ Add MODULE.FANS, MODULE.BUSINESS, MODULE.PROJECTS, MODULE.CAMPAIGNS, MODULE.CONTROL to permissions.js (or map to existing modules)

☐ Keep legacy deep links (/retail/, /cdp/) working via redirects

☐ Update @coxa/rbac seed / role defaults for new nav groups

Acceptance criteria: FanBox-trained staff can find all tools under expected menu names; permissions still enforced per role.

#### TASK-01-04 — Club-branded login (Coritiba / tenant theming)

Priority: P1 · Effort: S

☐ Support tenant logo, primary color, and custom login URL per club (Club model extension)

☐ Document deployment URL pattern (FanBox uses coritiba.fanbox.app.br)

Acceptance criteria: Coritiba tenant shows club branding on login; default Coxa branding for other tenants.

## 4. Section 02 — Dashboard Inicial

FanBox reference: fan base growth chart (new vs cumulative), engagement reports, spend reports, date range picker, chart download, CSV export, sortable columns, help tooltips.

### 4.1 Current state in Coxa

| Item | Status | Location |
| --- | --- | --- |
| Welcome / club KPI cards | Partial | OverviewPage — CDP event count, segment count only |
| Fan growth chart | Missing | — |
| Engagement reports | Missing | — |
| Spend reports | Missing | — |
| Period filter | Missing | — |
| CSV / chart export | Missing | — |

### 4.2 Tasks

#### TASK-02-01 — Fan base growth time-series API

Priority: P1 · Effort: M

☐ Create GET /api/v1/analytics/fan-growth?from=&to=&granularity=day|week|month

☐ Return series: { date, newRegistrations, cumulativeTotal }

☐ Source: FanProfile.createdAt grouped by period; include import batches if tracked

Acceptance criteria: Chart data matches manual count for seeded test data; empty periods return zero.

#### TASK-02-02 — Dashboard growth chart UI

Priority: P1 · Effort: M

☐ Replace or augment OverviewPage top section with dual-line chart (new registrations = light green, cumulative = dark green per FanBox manual)

☐ Date range picker (from / to)

☐ Download chart as PNG/SVG button

☐ Use lightweight chart library consistent with monorepo (e.g. Recharts — add to club-dashboard if not present)

Acceptance criteria: User can change period and see chart update; download produces usable image file.

#### TASK-02-03 — Engagement reports block

Priority: P1 · Effort: L

FanBox shows sortable engagement tables with CSV export and “?” help tooltips. Define Coxa engagement metrics aligned to available data:

| Report (proposed) | Data source |
| --- | --- |
| Active fans (30d) | CDP events or last activity trait |
| Ticket buyers (season) | Ticket / AttendanceRecord |
| Member check-ins | CheckInWindow / attendance |
| App opens | Future app event integration |
| Campaign participants | CampaignParticipation |
| Survey respondents | Projetos Digitais (TASK-05-xx) |

☐ Create GET /api/v1/analytics/engagement-reports?from=&to=

☐ Build report table component with column sort, CSV export, tooltip definitions

☐ Place below growth chart on OverviewPage

Acceptance criteria: Each report row links to “Ver Detalhes” drill-down (raw data table or export).

#### TASK-02-04 — Spend reports block

Priority: P1 · Effort: L

☐ Create GET /api/v1/analytics/spend-reports?from=&to=

☐ Aggregate by channel: retail POS, fan shop, F&B, membership fees, ticketing

☐ Metrics: total spend, avg ticket, unique buyers, spend by member tier

☐ UI: same table pattern as TASK-02-03 with sort + CSV + tooltips

Acceptance criteria: Totals reconcile with Sale, MembershipTransaction, and ticket purchase records.

## 5. Section 03 — Meus Fãs

FanBox reference: three sub-screens — Single Fan View, Engajamento, Informações Pessoais.

### 5.1 Single Fan View (3.1)

FanBox capabilities:

Search by: CPF, Name, Email, ID, Passport, Mobile

Contact + engagement summary row

Actions: send notification (email/push), edit registration

Profile fields: locality, gender, birthday, interaction channels, spend last month/year

Ticket purchases, membership plan

E-commerce purchases, TV Coxa Prime subscription

Coxa ID data, club relationship, brand consumption profile, digital products (favorite club, sports betting, social network)

#### TASK-03-01 — Expand Customer 360 search

Priority: P0 · Effort: M

☐ Extend GET /api/v1/cdp/customer-360 search to accept: cpf, fullName, email, fanId, passport, phone

☐ Update CdpCustomer360Page with multi-field search form (single input with type selector, or dedicated fields)

☐ Rename/navigate as Single Fan View under Meus Fãs

Acceptance criteria: All FanBox search keys return correct profile or clear “not found”.

#### TASK-03-02 — Single Fan View layout (FanBox rows)

Priority: P1 · Effort: L

Rebuild CdpCustomer360Page in FanBox row structure:

| Row | Content |
| --- | --- |
| Row 1 | Contact, engagement KPIs, notify + edit actions |
| Row 2 | Tickets purchased, membership plan status |
| Row 3 | E-commerce orders, OTT/subscription status |
| Row 4 | Coxa ID traits, club affinity, consumption profile, digital behavior |

☐ “Ver Detalhes” on each widget opens underlying data table (tickets list, orders list, etc.)

☐ Edit registration opens slide-over form (PATCH /api/v1/cdp/fan-profiles/:id)

☐ Notify actions stub → wired in TASK-07-xx

Acceptance criteria: FanBox manual figures 7–10 information hierarchy is reproduced with Coxa data.

#### TASK-03-03 — Per-fan spend windows

Priority: P1 · Effort: S

☐ Add to Customer 360 API: spendLast30DaysCents, spendLast365DaysCents by channel

☐ Display in Row 1 KPI cards

#### TASK-03-04 — Fan profile enrichment schema

Priority: P0 · Effort: M

Extend FanProfile (or companion FanDemographics model) with FanBox fields:

☐ cpf, passport, gender, birthDate

☐ Address: street, city, state, postalCode, country

☐ hasChildren, ageRange, householdIncomeBand (enum buckets)

☐ preferredSocialNetwork, sportsBetting, affinityClubId (other club sympathy)

☐ biometricRegistered (boolean — FanBox filter example)

☐ primaryInteractionChannels[] (app, email, stadium, e-commerce, etc.)

☐ Migration/seed update for demo profiles

Acceptance criteria: Fields editable in admin UI; populate counters (TASK-01-01) and filters (TASK-06-01).

### 5.2 Engajamento (3.2)

FanBox: duplicate of home dashboard — growth chart + engagement/spend reports.

#### TASK-03-05 — Fans > Engajamento page

Priority: P2 · Effort: S

☐ Create /fans/engagement reusing components from TASK-02-02, TASK-02-03, TASK-02-04

☐ No new backend if APIs shared

Acceptance criteria: Identical data to dashboard; accessible from Meus Fãs menu.

### 5.3 Informações Pessoais (3.3)

FanBox: aggregate profile distribution — locality, children, age band, household income, etc.

#### TASK-03-06 — Fan demographic profile dashboard

Priority: P1 · Effort: M

☐ Create GET /api/v1/analytics/fan-demographics returning histograms:

By city/state/country

Gender distribution

Age band distribution

Has children (yes/no/unknown)

Income band distribution

☐ Build /fans/profiles page with bar/pie charts per dimension

☐ Period filter optional (snapshot = current base)

Acceptance criteria: Charts reflect enriched profile data; empty fields bucketed as “Unknown”.

## 6. Section 04 — Negócios

FanBox reference: unified business analytics for 10 data sources, each with locality / gender / age breakdowns plus source-specific KPIs.

| FanBox source | Coxa mapping | Report status |
| --- | --- | --- |
| Sócio Torcedor | membership/* | Partial — member list exists; no analytics dashboard |
| Ingressos | ticketing/* | Partial — events/tickets ops; no sales analytics |
| Acesso | ticketing/check-in, AttendanceRecord | Partial |
| Lojas | retail/sales (physical locations) | Partial — sales list; no analytics |
| E-Commerce | retail/shop | Partial |
| App Oficial | fan-app events | Missing |
| OTT (TV Coxa Prime) | external integration | Missing |
| Coxa Run | product line / channel tag | Missing |
| Coxa Foods | fnb/sales | Partial — F&B dashboard exists |
| Manto da Glória | product category filter on retail | Missing |

### 6.1 Shared Negócios infrastructure

#### TASK-04-00 — Negócios layout shell

Priority: P1 · Effort: M

☐ Create /business layout with sub-nav tabs for all 10 sources

☐ Shared header: date range picker (FanBox: “alterar período no cabeçalho”)

☐ Shared demographic breakdown toggles: Localidade · Gênero · Faixa etária

☐ Shared CSV export + “?” metric definitions

#### TASK-04-01 — Sócio Torcedor analytics

Priority: P1 · Effort: L

FanBox KPIs: sectors list, check-in counts, adimplentes vs inadimplentes, tenure, total spend.

☐ API: GET /api/v1/analytics/business/membership?from=&to=

☐ UI: /business/membership

☐ Charts/tables: plan distribution, sector breakdown, compliance status, avg tenure, revenue

☐ Demographic slices on all widgets

Acceptance criteria: Numbers match FanMembership, MembershipTransaction, check-in records.

#### TASK-04-02 — Ingressos analytics

Priority: P1 · Effort: L

☐ API: GET /api/v1/analytics/business/tickets?from=&to=

☐ KPIs: recent purchases, tickets per match, tickets per sector, sales per match

☐ UI: /business/tickets

#### TASK-04-03 — Acesso (stadium access) analytics

Priority: P1 · Effort: M

☐ API: GET /api/v1/analytics/business/access?from=&to=

☐ KPIs: total entries, member vs non-member attendance, repeat visitors

☐ Source: AttendanceRecord, gate scan events

#### TASK-04-04 — Lojas (retail stores) analytics

Priority: P1 · Effort: M

☐ API: GET /api/v1/analytics/business/stores?from=&to=

☐ KPIs: sales by location, top products, spend per fan, transaction count

☐ Filter Sale where location.type = physical store

#### TASK-04-05 — E-Commerce analytics

Priority: P1 · Effort: M

☐ API: GET /api/v1/analytics/business/ecommerce?from=&to=

☐ KPIs: top products, average ticket, buyers by membership plan

☐ Source: fan shop channel sales

#### TASK-04-06 — App Oficial analytics

Priority: P2 · Effort: L

☐ Define app event schema (app.session, app.screen_view, platform android/ios)

☐ Ingest from fan-app → CDP

☐ API + UI: /business/app — DAU/MAU, platform split, version adoption

#### TASK-04-07 — OTT / streaming analytics

Priority: P3 · Effort: L

☐ Integration adapter for TV Coxa Prime (or generic OTT webhook)

☐ Model: OttSubscription linked to FanProfile

☐ API + UI: /business/ott — active subs, churn, viewing engagement

#### TASK-04-08 — Coxa Run analytics

Priority: P3 · Effort: M

☐ Tag products/events with channel: coxa_run or dedicated product category

☐ API + UI: /business/coxa-run — kits sold, plans, total orders

#### TASK-04-09 — Coxa Foods analytics

Priority: P1 · Effort: S

☐ Extend existing FnbSalesDashboardPage metrics into /business/coxa-foods

☐ Add FanBox KPIs: items sold, revenue by match day, top items

☐ Demographic breakdowns per TASK-04-00

#### TASK-04-10 — Manto da Glória analytics

Priority: P2 · Effort: M

☐ Product category or collection filter for “Manto da Glória” SKUs

☐ API + UI: /business/manto — units sold, models ranking, member vs non-member buyers

#### TASK-04-11 — External integrations backlog

Priority: P3 · Effort: XL

FanBox notes: Bomache e-commerce integrated; Bling not yet integrated.

☐ Document integration priority: Bomache, Bling, Coxa Prime, legacy FanBox CSV formats

☐ Build connector framework under backend/src/integrations/

☐ Idempotent import → CDP events + domain records

## 7. Section 05 — Projetos Digitais

FanBox reference: Pesquisas, Votações, Sorteios, Concursos, Outros Projetos (NPS).

Current state: No routes, models, or UI in Coxa for these features. CampaignParticipation exists but is not a full project engine.

### 7.1 Shared project engine

#### TASK-05-00 — Digital projects domain model

Priority: P3 · Effort: L

☐ Models: DigitalProject (type: survey | vote | raffle | contest | nps), ProjectQuestion, ProjectResponse, ProjectSubmission (contest attachments)

☐ Status lifecycle: draft → scheduled → active → closed → archived

☐ Link responses to FanProfile; emit survey.completed, vote.cast, raffle.entered, contest.submitted CDP events

☐ Survey answers map to fan profile enrichment fields (FanBox: “pesquisas preenchem Single Fan View”)

#### TASK-05-01 — Pesquisas (Surveys)

Priority: P3 · Effort: L

☐ Admin UI: /projects/surveys — list, create, view results

☐ Question types: single choice, multi, text, scale, date

☐ Fan-facing form in fan-dashboard or public link with auth

☐ Export / print results (PDF or CSV)

☐ Map answer keys → profile traits (configurable mapping table)

Acceptance criteria: Completing survey updates Single Fan View fields within 1 trait refresh cycle.

#### TASK-05-02 — Votações (Votes)

Priority: P3 · Effort: M

☐ Admin UI: /projects/votes — create vote, options, schedule, status tabs (in progress / scheduled / closed)

☐ Fan UI: cast one vote per fan per project

☐ Results view with percentages and participation count

☐ Example use case: Manto da Glória design selection (per manual)

#### TASK-05-03 — Sorteios (Raffles)

Priority: P3 · Effort: M

☐ Admin UI: /projects/raffles — create raffle, eligibility rules (e.g. members only)

☐ Participant list view; winner draw action (random, auditable seed)

☐ Winner list export

#### TASK-05-04 — Concursos (Contests)

Priority: P3 · Effort: L

☐ Admin UI: /projects/contests — create contest with custom form fields + file upload

☐ Submissions list; double-click opens submission detail (FanBox behavior)

☐ File storage (S3 or local dev bucket)

#### TASK-05-05 — Outros Projetos / NPS

Priority: P3 · Effort: M

☐ NPS project type with 0–10 score + optional comment

☐ Post-sale trigger hook (retail sale completed → send NPS link)

☐ Aggregate NPS dashboard widget

## 8. Section 06 — Fan Intelligence

FanBox reference: Filtros (combinable filters on all Single Fan View fields, export CSV, save filter) and Meus Insights (reports from saved filters).

### 8.1 Current state in Coxa

| Item | Status | Location |
| --- | --- | --- |
| Trait-based segment builder | Partial | CdpSegmentsPage, Segment model |
| Combinable multi-field filters | Missing | — |
| Save named filters | Missing | — |
| Export filter results CSV | Missing | — |
| Insights dashboard | Missing | — |

### 8.2 Tasks

#### TASK-06-01 — Advanced filter builder

Priority: P2 · Effort: L

☐ Create SavedFilter model: { name, rules[], createdBy, tenantId }

☐ Rule schema: { field, operator, value } covering all FanProfile + trait + membership + ticket + spend fields

☐ UI: /intelligence/filters — visual filter builder with AND combination (FanBox: “centenas de filtros combinados”)

☐ Preview count before export

☐ Examples from manual: biometria cadastrada + sócio > 1 ano + behavior flags

Acceptance criteria: Filter preview count matches exported CSV row count.

#### TASK-06-02 — Export filtered fan list

Priority: P2 · Effort: M

☐ POST /api/v1/intelligence/filters/:id/export → CSV stream

☐ Columns: configurable; default contact + key traits

☐ Rate limit / async job for large exports (>50k rows)

#### TASK-06-03 — Save & manage filters

Priority: P2 · Effort: S

☐ Save filter button (FanBox: blue button)

☐ List saved filters with last run count and date

☐ Edit / duplicate / delete

#### TASK-06-04 — Meus Insights dashboard

Priority: P2 · Effort: M

☐ /intelligence/insights — pin saved filters as insight cards

☐ Each card: fan count, trend vs previous period, top 3 breakdown dimensions

☐ Optional scheduled refresh

#### TASK-06-05 — Bridge saved filters to segments

Priority: P2 · Effort: S

☐ “Promote to segment” action creates/updates Segment from SavedFilter rules

☐ Keeps compatibility with personalization / offers module

## 9. Section 07 — Campanhas

FanBox reference: create/edit/send mass email, SMS, push campaigns; recipient selection via saved filters; schedule or send immediately; templates with drag-and-drop builder; campaign analytics (sent, opened, etc.).

### 9.1 Current state in Coxa

| Item | Status |
| --- | --- |
| CampaignParticipation model | Exists — participation tracking only |
| Campaign CRUD | Missing |
| Email/push delivery | Missing |
| Template builder | Missing |

### 9.2 Tasks

#### TASK-07-01 — Campaign domain model

Priority: P4 · Effort: L

☐ Models: Campaign, CampaignTemplate, CampaignDelivery, CampaignMetric

☐ Campaign fields: name, type (email | sms | push), status (draft | scheduled | sending | sent | cancelled)

☐ Content: subject, sender, templateId, body snapshot

☐ Recipients: savedFilterId or segmentId

☐ Schedule: scheduledAt optional

#### TASK-07-02 — Nova Campanha wizard

Priority: P4 · Effort: L

FanBox steps: name/type → content → recipients → review → send/schedule

☐ UI: /campaigns/new multi-step wizard

☐ Recipient step: pick saved filter (TASK-06-03)

☐ Review step: audience size, sample recipients, send test

#### TASK-07-03 — Minhas Campanhas list

Priority: P4 · Effort: M

☐ UI: /campaigns — tabs: drafts, scheduled, sent

☐ Sent campaigns: “Visualizar” opens delivery analytics

#### TASK-07-04 — Campaign analytics

Priority: P4 · Effort: M

☐ Track: sent, delivered, opened, clicked, bounced, unsubscribed (email); delivered, opened (push)

☐ Webhook handlers for email provider (SendGrid/SES) and push (FCM/APNs)

☐ UI mirrors FanBox figures 37–38

#### TASK-07-05 — Email template manager

Priority: P4 · Effort: XL

☐ UI: /campaigns/templates — list, create, edit, delete

☐ Create options: blank (drag-and-drop builder), duplicate existing, import HTML

☐ Builder: blocks for text, image, button, fan merge tags ({{fan.firstName}})

☐ Preview + download HTML

#### TASK-07-06 — Notification delivery services

Priority: P4 · Effort: L

☐ emailService — queue + provider integration

☐ pushService — fan-app device tokens

☐ smsService — optional provider stub

☐ Background worker (Bull/BullMQ or cron) for scheduled sends

☐ Wire Single Fan View “notify” buttons (TASK-03-02) to one-off send using templates

#### TASK-07-07 — Single Fan View quick actions

Priority: P4 · Effort: S

☐ Email / push buttons on Customer 360 (FanBox yellow buttons)

☐ Opens compose modal with fan pre-selected

## 10. Section 08 — Painel de Controle

FanBox reference: Gestão de Contas (user CRUD + permissions) and Importar arquivo (CSV import for multiple entity types).

### 10.1 Gestão de Contas

#### TASK-08-01 — Account management parity

Priority: P0 · Effort: S

| FanBox capability | Coxa status |
| --- | --- |
| Create user | Done — UsersPage invite |
| Edit user | Done — role update |
| Delete user | Verify — add deactivate/remove if missing |
| Permission scopes per module | Partial — role-based; add fine-grained module toggles if required |

☐ Audit UsersPage against FanBox permission matrix

☐ Add UI for module-level access toggles per user (if not covered by roles)

☐ Move under /control/users with FanBox labeling

Acceptance criteria: Club admin can manage staff accounts without developer intervention.

### 10.2 Importar arquivo

FanBox supported import types:

Cadastros (registrations)

Planos de Assinatura

Ingressos e Acessos

Compra de Produtos/Serviços

Eventos

Status de Planos de Assinatura

Eventos do App

Leads

#### TASK-08-02 — CSV import framework

Priority: P0 · Effort: L

☐ UI: /control/import — upload CSV, select import type, preview, confirm

☐ Backend: POST /api/v1/import/:type with validation report

☐ Job tracking: { importId, status, rowsOk, rowsFailed, errorLog[] }

☐ Idempotency via external reference column

#### TASK-08-03 — Import type implementations

Priority: P0 · Effort: XL (split per type)

| Import type | Target model(s) | Priority |
| --- | --- | --- |
| Cadastros | FanProfile + demographics | P0 |
| Planos de Assinatura | MembershipPlan | P1 |
| Ingressos e Acessos | Ticket, AttendanceRecord | P1 |
| Compra Produtos/Serviços | Sale | P1 |
| Eventos | MatchEvent, CdpEvent | P1 |
| Status Planos | FanMembership status | P1 |
| Eventos do App | CdpEvent | P2 |
| Leads | FanProfile (status=lead) | P2 |

☐ Publish CSV templates per type (docs/import-templates/*.csv)

☐ FanBox migration: document column mapping from legacy exports

Acceptance criteria: Import 10k registration rows without duplicate fan IDs; failed rows downloadable as error CSV.

## 11. Cross-cutting tasks

#### TASK-X-01 — Trait calculator expansion

Priority: P1 · Effort: M

☐ Extend traitCalculator.js for new profile fields, spend windows, membership tenure, biometric flag

☐ Ensure traits power filters (TASK-06-01) and segments

#### TASK-X-02 — API client & permissions update

Priority: P0 · Effort: M

☐ Add all new endpoints to apps/club-dashboard/src/lib/api.js

☐ Register modules in TenantConfig.enabledModules seed

☐ Update ProtectedRoute / ModuleRoute for new paths

#### TASK-X-03 — i18n (PT-BR / EN)

Priority: P2 · Effort: M

FanBox manual is Portuguese. Coritiba ops expect PT-BR labels.

☐ Extract FanBox-facing strings to i18n dictionary

☐ Default PT-BR for Coritiba tenant; EN fallback

#### TASK-X-04 — Documentation & training

Priority: P2 · Effort: S

☐ Update CLIENT_FEATURES.md with FanBox parity section

☐ Produce Coxa operational manual mirroring FanBox section numbers for staff training

#### TASK-X-05 — E2E test plan

Priority: P2 · Effort: M

☐ Smoke tests: login → counters → search fan → export filter → import CSV

☐ Regression suite for existing retail/ticketing/membership flows after nav restructure

## 12. Dependency graph (critical path)

flowchart TD
  T0104[TASK-03-04 Profile schema]
  T0101[TASK-01-01 Counter API]
  T0102[TASK-01-02 Counter bar]
  T0802[TASK-08-02 Import framework]
  T0803[TASK-08-03 Import types]
  T0301[TASK-03-01 Search expansion]
  T0201[TASK-02-01 Growth API]
  T0400[TASK-04-00 Negócios shell]
  T0601[TASK-06-01 Filter builder]
  T0701[TASK-07-01 Campaign model]

  T0104 --> T0101
  T0104 --> T0301
  T0104 --> T0601
  T0802 --> T0803
  T0803 --> T0101
  T0101 --> T0102
  T0201 --> T0400
  T0601 --> T0701

Critical path for demo parity: TASK-03-04 → TASK-08-02 → TASK-01-01 → TASK-03-01 → TASK-02-01 → TASK-04-00

## 13. Effort legend

| Size | Indicative effort |
| --- | --- |
| S | 0.5–1 day |
| M | 2–3 days |
| L | 4–8 days |
| XL | 2+ weeks |

## 14. Out of scope (this document)

Replacing FanBox production URL (coritiba.fanbox.app.br) — deployment task per AWS_DEPLOYMENT.md

Full Bomache/Bling/e-commerce connector build (tracked in TASK-04-11)

Fan mobile app rebuild (only analytics ingestion in TASK-04-06)

Data migration execution from FanBox production DB (separate migration runbook)

## 15. Task index (quick reference)

| ID | Title | Phase | Due by |
| --- | --- | --- | --- |
| TASK-01-01 | Global fan counter API | P0 | 12 Jun 2026 |
| TASK-01-02 | Persistent counter bar | P0 | 12 Jun 2026 |
| TASK-01-03 | FanBox sidebar IA | P0 | 12 Jun 2026 |
| TASK-01-04 | Tenant login branding | P1 | 16 Jun 2026 |
| TASK-02-01 | Fan growth time-series API | P1 | 14 Jun 2026 |
| TASK-02-02 | Dashboard growth chart | P1 | 15 Jun 2026 |
| TASK-02-03 | Engagement reports | P1 | 16 Jun 2026 |
| TASK-02-04 | Spend reports | P1 | 16 Jun 2026 |
| TASK-03-01 | Expand Customer 360 search | P0 | 11 Jun 2026 |
| TASK-03-02 | Single Fan View layout | P1 | 15 Jun 2026 |
| TASK-03-03 | Per-fan spend windows | P1 | 15 Jun 2026 |
| TASK-03-04 | Fan profile enrichment schema | P0 | 11 Jun 2026 |
| TASK-03-05 | Fans > Engajamento page | P2 | 18 Jun 2026 |
| TASK-03-06 | Demographic profile dashboard | P1 | 16 Jun 2026 |
| TASK-04-00 | Negócios layout shell | P1 | 14 Jun 2026 |
| TASK-04-01 … 04-05, 04-09 | Core business analytics | P1 | 16 Jun 2026 |
| TASK-04-06 … 04-11 | Extended integrations / analytics | P3 | 19 Jun 2026 (fallback: defer) |
| TASK-05-00 … 05-03 | Surveys, votes, raffles | P3 | 19 Jun 2026 |
| TASK-05-04 … 05-05 | Contests, NPS | P3 | 19 Jun 2026 (fallback: defer) |
| TASK-06-01 … 06-05 | Fan Intelligence | P2 | 18 Jun 2026 |
| TASK-07-01 … 07-07 | Campanhas | P4 | 20 Jun 2026 |
| TASK-08-01 | Account management parity | P0 | 12 Jun 2026 |
| TASK-08-02 … 08-03 | CSV import | P0 | 12 Jun 2026 |
| TASK-X-01 … X-05 | Cross-cutting | P0–P2 | 18 Jun 2026 |

Document generated from Manual do FanBox (Coritiba SAF, v1.0) mapped against Coxa repository state — June 2026.

Final delivery deadline: Friday, 20 June 2026.